Doggy dog world Pty Ltd

Project PuppyDock ramp

Phase 0 & 1

Proposal Reference:  26-210203,3

Attention:  		Maia & Eran

Author:  		Marco Sebastiani, Tony PanettaClick or tap here to enter text.

Submission Date:  	21 February 2026

Executive Summary

Doggy Dog World is developing a swimming pool ramp that enables dogs to safely and easily exit swimming pools.

Through a carefully considered design architecture and well-informed decisions around geometry, materials, color selection, and system assembly, PuppyDock aims to position itself as the market-leading solution for this application. Existing products currently available are generally of significantly lower quality and sophistication, both in design execution and overall performance.

Doggy Dog World has requested a proposal for developing:

- An updated design that is able to withstand larger size dogs (about 30Kgs in weight)

- Tooling development and subsequent manufacturing of the PuppyDock ramp  throughout the launch, ramp-up and steady state manufacturing stages.

Paniani Products Pty Ltd is a tech innovation, sourcing and manufacturing management company specializing in the development of high-performance products and is uniquely positioned to be Doggy Dog World’s partner of choice for development of PuppyDock.

Figure 1: PuppyDock adjustable ramp

# Development Approach

This proposal outlines the activities associated with the design phase (Phase 0) and the subsequent manufacturing phase (Phase 1) for the PuppyDock product.

The development approach will adopt a top-down, risk-based methodology, beginning with the alignment of Paniani Products and Doggy Dog World on all product requirements, critical characteristics, and performance expectations. This will include a structured definition of functional requirements, design constraints, and the full set of “wants” and “needs” for PuppyDock.

Given Doggy Dog World’s request for a design that is both more robust (to support larger dogs) and more cost-effective at higher production volumes, the initial phase will focus on systematically identifying and mitigating key technical and commercial risks.

This will be achieved through an in-person workshop and brainstorming session, where both parties will collaboratively:

- Review existing product limitations

- Define critical-to-quality (CTQ) requirements

- Identify risk areas related to strength, stability, materials, and manufacturing cost

- Explore candidate design strategies to address robustness and scalability

Following this requirement and risk alignment phase, the two companies will converge on a single preferred concept direction, which will then be progressed into detailed design by Paniani Products for Phase 0 execution.

If additional scope is identified during the course of the project, (such as new design requests, change of mind, additional features or components, research of new materials and any other additional request that adds to the workload) Paniani Products will provide a separate quotation for the additional work at a standard hourly rate of AUD 130 per hour. (GST excluded)

No additional work will be undertaken without prior written communication to, and approval from, Doggy Dog World.

# Program of Work

## Objectives

The objectives of the two phases of work are as follows:

Phase 0 – Design and Risk Reduction

- Identify and select a solution concept that satisfies the updated strength requirements and cost-reduction objectives.

- Redesign the Puppy Dock product using CAD best-practice methodologies, ensuring the design is optimized for manufacturability (DFM).

- De-risk key technical challenges, including material selection, dynamic loading performance, and UV resistance.

Phase 1 – Tooling

- Upon completion of Phase 0, Paniani Products will provide an updated quotation for tooling and manufacturing of PuppyDock to reflect any updates in design, materials and technologies selected.

- Prototype at least one complete PuppyDock set using materials representative of the final production specification (to be shared between both companies for evaluation and review).

- Initiate final DFM, Tooling design and manufacturing, manage qualification of individual components and the overall assembly, implement any required design improvements, and prepare standard operating procedures (SOPs) for later manufacturing.

- Establish manufacturing capability and associated logistics in alignment with Doggy Dog World’s production volume forecasts and geographical needs.

Phase 2 – Manufacturing

- Upon completion of Phase 0, Paniani Products will provide a revised proposal reflecting the costs of manufacturing of PuppyDock after confirmation of materials, schedule and logistic details.

## Activities & Deliverables

Table 1: Activities

| ID | Activity Description | Output |
| --- | --- | --- |
| 1 | Project Initiation Paniani Products will develop a range of concepts aimed at increasing strength while reducing cost and will submit these to Doggy Dog World for review. Following the review, both parties will work collaboratively to select the most suitable option or identify alternative solutions that meet the stated requirements. This process may require several iterations before an agreed approach is reached. | - New concept ideas for meeting strength and cost requirements - Agreement on concept design to be brought forward - List of requirements for qualification of the parts - Preliminary Risk watchlist |
| 2 | Detailed design Paniani Products will redesign the Puppy Dock ramp using CAD best-practice methodologies and incorporating Design for Manufacturability (DFM) principles. The concept agreed in Activity 1 will be developed into a fully defined engineering design. | - 3D CAD Datapack - 2D manufacturing drawings - DFM report - SOP documents |
| 3 | Prototyping Following review and approval of the detailed design, Doggy Dog World will procure a prototype set of parts (with Paniani Products providing procurement support if required). Material selection will be carefully managed to ensure prototype performance is representative of the final production product. Functional testing will be conducted and results assessed. | - Assessment report by Paniani - Implementation of any required changes to the CAD model and other technical specification - Confirmation of tooling and production cost |
| 4 | Tooling Paniani Products will manage the tooling phase with a qualified tooling and injection moulding supplier located in Guangdong Province, China. Paniani Products will act as the primary liaison between Doggy Dog World and the manufacturer throughout tooling development and parts qualification. Regular progress reporting will be provided covering tooling design, schedule status, trial outcomes, and technical issues as required. | - Plastic tooling completed as per Appendix 1 - Weekly progress and status reports - Qualification documentation (FAI through to final approval) |

# Schedule

The program of work outlined in this proposal is expected to commence upon authorisation and be completed over a period of 1 month for Phase 0 and on-going for Phase 1.

# Budget

The total estimate for the 2 phases of work as outlined above is:

## Phase 0 budget estimate

| # | Activity | AUD |
| --- | --- | --- |
| 1 | Project Initiation | FOC |
| 2 | Detailed design | $5,000 |
|  | TOTAL | $5,000 |

Note: Prices are exclusive of GST

## Phase 1 budget estimate

Pricing subject to output from Phase 0

| # | Activity | USD |
| --- | --- | --- |
| 3 | Rapid Prototyping (borne by Doggy Dog World) | TBC |
| 4 | Tooling estimate | 89,300 |
|  | TOTAL | $89,300 |

Note: Prices are exclusive of GST

All material and expense costs for Phase 1 are quoted in USD, reflecting the currency used in the country of manufacture. Final invoicing and payment will be converted to AUD using the prevailing exchange rate on the invoice issue date.

# Assumptions & Qualifications

The key assumptions and qualifications that have been made in preparing the Program of Work and corresponding Budget and Schedule are:

- Paniani Products will provide one weekly progress meeting at no charge (FOC). Any additional meetings requested by Doggy Dog World will be charged at the standard hourly rate of AUD 130 per hour (excluding GST).

- Doggy Dog World will be responsible for all prototyping costs as described in Activity #3.

- Safety and compliance testing expenses are not included – if required, Doggy Dog World is responsible for any relevant charges.

- Costs associated with certification, and regulatory compliance testing are excluded from this proposal. Where such testing is required, Doggy Dog World will be responsible for all related expenses.

- Doggy Dog World is solely responsible for ensuring that the product complies with all applicable regulations, standards, and legal requirements necessary for sale and distribution in any intended market or country

- Paniani Products shall not be responsible or liable for the use, misuse, or operation of the product by end users. This includes, but is not limited to, any claims, complaints, damages, losses, injuries, or legal actions arising from customer use, improper installation, unintended application, or any unforeseen events associated with the product once it has been released to markets.

- Paniani Products shall act as the primary contractor for this project. Any subcontractors engaged will operate under Paniani Products’ terms and conditions.

# Standard Terms

## Scope Management

Paniani Products has drawn upon many years of product development experience and expertise to provide a realistic estimate of the development budget and schedule. Estimates are based on many assumptions including a “success basis”, which assumes that each development activity will be done once with a successful outcome first time. In the event of unexpected project requirements, unanticipated outcomes, or incorrect assumptions there may be cause for variations in scope and budget such as reallocation of effort between tasks or maturity of outputs. This will be discussed with Doggy Dog World representative at the regular weekly project meetings and documented in the minutes. Paniani Products is entitled to rely on the client representative as having the requisite authority to approve the changes on behalf of Doggy Dog World, unless, within 14 days of receiving a copy of the minutes from the meeting, Doggy Dog World informs Paniani Products that they disagree with the approval given at the meeting. This clause applies notwithstanding any inconsistent clause in the Terms of Business.

## Invoicing Schedule and Payment Terms

The program of work will be completed on a “time-and-materials basis,” where only
actual hours worked are invoiced. Doggy Dog World will be invoiced for less than the estimate in this proposal in the event that the program of work is completed with less effort than estimated. If, on the other hand, activities in the program of work are expected to require more effort than initially estimated, Paniani products shall advise Doggy Dog World consistent with the scope management terms as described above.

Paniani Products will provide regular progress updates in delivering all agreed outputs and the project fees spend rate to ensure that the budget is tightly managed and controlled.

Invoices shall be issued in AUD according to the invoice schedule below.

Invoicing Schedule & Payment Terms

- PHASE 0 Design Scope: 100% payable prior to commencement.

- PHASE 1 Tooling:  50% Deposit at Start, 30% before dispatching first off-tool-sample, 20% balance upon sample approval.

- PHASE 1 Manufacturing:   50% deposit at purchase order, 30% before dispatch from manufacturer, 20% 30 days after receiving invoice from Paniani Products.

## Validity

This proposal is valid for a period of 28 days from the date of submission.

# Authorisation to Proceed

To:  Maia & Eran Marsch

Doggy Dog World Pty Ltd

Five Dock, NSW, AUSTRALIA 2046

p. +61 402 398 841

e.	eran@doggydogworld.com.au

maia@doggydogworld.com.au

Proposal Reference: 26-210203, 3

We have read and agreed with this proposal and the Terms of Business and hereby authorise Planet Innovation to undertake the program of work as described in this proposal:

| Name: |  |
| --- | --- |
| Title: |  |
| Signature: |  |
| Company: | Doggy dog world Pty Ltd |
| Date: |  |

Proposal Authorisation:

| Name: |  |
| --- | --- |
| Title: |  |
| Signature: |  |
| Company: | Paniani Products Pty Ltd |
| Date: |  |